## ProjectSchedule
Branxton BESS Construction Traffic Volumes
|  |  |  | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 | [6 empty] | WEEK 12 | [6 empty] | WEEK 13 | [6 empty] | WEEK 14 | [6 empty] | WEEK 15 | [6 empty] | WEEK 16 | [6 empty] | WEEK 17 | [6 empty] | WEEK 18 | [6 empty] | WEEK 19 | [6 empty] | WEEK 20 | [6 empty] | WEEK 21 | [6 empty] | WEEK 22 | [6 empty] | WEEK 23 | [6 empty] | WEEK 24 | [6 empty] | WEEK 25 | [6 empty] | WEEK 26 | [6 empty] | WEEK 27 | [6 empty] | WEEK 28 | [6 empty] | WEEK 29 | [6 empty] | WEEK 30 | [6 empty] | WEEK 31 | [6 empty] | WEEK 32 | [6 empty] | WEEK 33 | [6 empty] | WEEK 34 | [6 empty] | WEEK 35 | [6 empty] | WEEK 36 | [6 empty] | WEEK 37 | [6 empty] | WEEK 38 | [6 empty] | WEEK 39 | [6 empty] | WEEK 40 | [6 empty] | WEEK 41 | [6 empty] | WEEK 42 | [6 empty] | WEEK 43 | [6 empty] | WEEK 44 | [6 empty] | WEEK 45 | [6 empty] | WEEK 46 | [6 empty] | WEEK 47 | [6 empty] | WEEK 48 | [6 empty] | WEEK 49 | [6 empty] | WEEK 50 | [6 empty] | WEEK 51 | [6 empty] | WEEK 52
Mobilisation, Materials and Track Upgrades | Total Number of Deliveries
Site Preparation and Mobilisation | 12 | WEEK 1 | WEEK 3 | 0.85714 | 0.85714 | 0.85714 | 0.85714 | 0.85714 | 0.85714 | 0.85714 | 0.85714 | 0.85714 | 0.85714 | 0.85714 | 0.85714 | 0.85714 | 0.85714
Client Temporary Construction Area | 65 | WEEK 3 | WEEK 5 | [14 empty] | 3.0952 | 3.0952 | 3.0952 | 3.0952 | 3.0952 | 3.0952 | 3.0952 | 3.0952 | 3.0952 | 3.0952 | 3.0952 | 3.0952 | 3.0952 | 3.0952 | 3.0952 | 3.0952 | 3.0952 | 3.0952 | 3.0952 | 3.0952 | 3.0952
Upgrading and Constructing Access Tracks | 1950 | WEEK 6 | WEEK 23 | [35 empty] | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107
Material Delivery for construction of Site Boundary Fencing and Security Columns | 14 | WEEK 3 | WEEK 6 | [14 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
SPT Temporary Construction Compound | 55 | WEEK 22 | WEEK 25 | [147 empty] | 1.9643 | 1.9643 | 1.9643 | 1.9643 | 1.9643 | 1.9643 | 1.9643 | 1.9643 | 1.9643 | 1.9643 | 1.9643 | 1.9643 | 1.9643 | 1.9643 | 1.9643 | 1.9643 | 1.9643 | 1.9643 | 1.9643 | 1.9643 | 1.9643 | 1.9643 | 1.9643 | 1.9643 | 1.9643 | 1.9643 | 1.9643 | 1.9643
Component Delivery and Construction of Ancillary Buildings
Material delivery for Client Control Building, Engineering Building and SPT Control Building | 57 | WEEK 21 | WEEK 26 | [140 empty] | 1.3571 | 1.3571 | 1.3571 | 1.3571 | 1.3571 | 1.3571 | 1.3571 | 1.3571 | 1.3571 | 1.3571 | 1.3571 | 1.3571 | 1.3571 | 1.3571 | 1.3571 | 1.3571 | 1.3571 | 1.3571 | 1.3571 | 1.3571 | 1.3571 | 1.3571 | 1.3571 | 1.3571 | 1.3571 | 1.3571 | 1.3571 | 1.3571 | 1.3571 | 1.3571 | 1.3571 | 1.3571 | 1.3571 | 1.3571 | 1.3571 | 1.3571 | 1.3571 | 1.3571 | 1.3571 | 1.3571 | 1.3571 | 1.3571
Material delivery for construction of battery foundations | 1000 | WEEK 27 | WEEK 50 | [182 empty] | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524 | 5.9524
MV Switchgear Deliveries | 36 | WEEK 27 | WEEK 30 | [182 empty] | 1.2857 | 1.2857 | 1.2857 | 1.2857 | 1.2857 | 1.2857 | 1.2857 | 1.2857 | 1.2857 | 1.2857 | 1.2857 | 1.2857 | 1.2857 | 1.2857 | 1.2857 | 1.2857 | 1.2857 | 1.2857 | 1.2857 | 1.2857 | 1.2857 | 1.2857 | 1.2857 | 1.2857 | 1.2857 | 1.2857 | 1.2857 | 1.2857
Battery Container Deliveries | 550 | WEEK 29 | WEEK 52 | [196 empty] | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738
Grid Transformers | 12 | WEEK 25 | WEEK 32 | [168 empty] | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429 | 0.21429
Estimated Number of Deliveries per day |  |  |  | 0.85714 | 0.85714 | 0.85714 | 0.85714 | 0.85714 | 0.85714 | 0.85714 | 0.85714 | 0.85714 | 0.85714 | 0.85714 | 0.85714 | 0.85714 | 0.85714 | 3.5952 | 3.5952 | 3.5952 | 3.5952 | 3.5952 | 3.5952 | 3.5952 | 3.5952 | 3.5952 | 3.5952 | 3.5952 | 3.5952 | 3.5952 | 3.5952 | 3.5952 | 3.5952 | 3.5952 | 3.5952 | 3.5952 | 3.5952 | 3.5952 | 17.9107 | 17.9107 | 17.9107 | 17.9107 | 17.9107 | 17.9107 | 17.9107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 17.4107 | 18.7679 | 18.7679 | 18.7679 | 18.7679 | 18.7679 | 18.7679 | 18.7679 | 3.3214 | 3.3214 | 3.3214 | 3.3214 | 3.3214 | 3.3214 | 3.3214 | 3.3214 | 3.3214 | 3.3214 | 3.3214 | 3.3214 | 3.3214 | 3.3214 | 3.3214 | 3.3214 | 3.3214 | 3.3214 | 3.3214 | 3.3214 | 3.3214 | 3.5357 | 3.5357 | 3.5357 | 3.5357 | 3.5357 | 3.5357 | 3.5357 | 1.5714 | 1.5714 | 1.5714 | 1.5714 | 1.5714 | 1.5714 | 1.5714 | 7.4524 | 7.4524 | 7.4524 | 7.4524 | 7.4524 | 7.4524 | 7.4524 | 7.4524 | 7.4524 | 7.4524 | 7.4524 | 7.4524 | 7.4524 | 7.4524 | 10.7262 | 10.7262 | 10.7262 | 10.7262 | 10.7262 | 10.7262 | 10.7262 | 10.7262 | 10.7262 | 10.7262 | 10.7262 | 10.7262 | 10.7262 | 10.7262 | 9.4405 | 9.4405 | 9.4405 | 9.4405 | 9.4405 | 9.4405 | 9.4405 | 9.4405 | 9.4405 | 9.4405 | 9.4405 | 9.4405 | 9.4405 | 9.4405 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 9.2262 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738 | 3.2738
Minimum Number of Deliveries per day |  |  |  | 0.85714
Maximum Number of Deliveries per day |  |  |  | 18.7679
Average Number of Deliveries pre day |  |  |  | 10.3049